## Sheet1
ISSUE# | DESCRIPTION | PROJECT | OWNER | ETA | PRIORITY | COMMENT
ESHOP-3235 |  | 484 | Bhavya |  |  | NO ISSUE
ESHOP-3234 |  | 484 | Chetan |  |  | NO ISSUE
ESHOP-3240 |  | STEP2 | Nikhil | 2017-06-29 | Minor | ISSUE FIXED. Build yet to be released.
ESHOP-3224 |  | STEP2 | SUPPORT | NO ETA
ESHOP-3238 |  | STEP2 | Bhavya | 2017-06-30 | Minor | Yet to be fixed.
ESHOP-3239 |  | 484 | Chetan |  |  | Fixed and released.
ESHOP-3237 |  | STEP2 |  |  |  | Expected behaviour as per prod
ESHOP-3236 |  | 484 | Chetan | 2017-06-30 | Minor | To be verified in PROD.
ESHOP-3232 |  | 484 | Ashok | 2017-06-29 | Minor | What was the blocker to not close it by 29-June-2017?
ESHOP-3231 |  | STEP2 | SOA
ESHOP-3229 |  | STEP2 | Bhavya | 2017-06-30 | Major | Resolved
ESHOP-3223 |  | STEP2 | Bhavya |  |  | Resolved
ESHOP-3221 |  | 484 | Ashok |  |  | Test Data issue
ESHOP-3220 |  | 484 | Ashok | 2017-06-29 | Medium | Resolved
ESHOP-3219 |  | STEP2 | Ashok |  |  | Fixed and Released.
ESHOP-3216 |  | 484 | Bhavya |  |  | Fixed and Released.
ESHOP-3214 |  | STEP2 | Portal Support
ESHOP-3213 |  | 484 | Chetan | 2017-06-29 | Minor | Issue identified. Build to be released.
ESHOP-3209 |  | STEP2 | Nikhil |  |  | No changes
ESHOP-3242 |  | 484 | Chetan | 2017-06-29 | Major | Fixed and released.
NO JIRA | http://www.int.three.ie/shop/view/product/ql_catalog/catdevice/IP5S16GBGREY?tariffType=PAYG&journeyType=FTC no buttons displayed | STEP2 | Nikhil | 2017-06-30 | Major
NO JIRA | EPORTING Page. Remove THREE from the list | STEP2 | Nikhil | 2017-06-30 | Minor
NO JIRA | 3D Secure not working in INT. Refer https://developer.realexpayments.com/#!/technical-resources/test-card for test cards | STEP2 | Bhavya | 2017-06-30 | Major